## Sheet1
D05 - ANFORA |  |  |  | 1 March – 31 August 2026
CODE | INDICATOR NAME | BASELINE | TARGET | DATA VALUE | COMMENTS
NBS4.20 | Water Exploitation Index | Guadalquivir basin WEI+ baseline to be retrieved from Eurostat/CHG at project start (M1). Andalucía is classified by the EEA as a water-scarce region with recurrent structural water stress. | 10-15% |  | Not measured. No matched territorial WEI+ observation and baseline are available for this reporting scope. Municipal 2024 water volumes are contextual, not WEI+ or attributable ANFORA impact. Required: comparable water use and renewable resources for the same geography and annual/seasonal reference. Lasith must clarify the official ratio/target mapping. Source: retained official water-source review. DATA VALUE is blank because no defensible numerical result is available.
NBS15.1 | Citizen involvement in environmental education activities (Total) | 0 (no ANFORA-led training activities prior to M13). | 50 trained users | 0 | Declared result: 0 persons trained. Evenor-Tech confirms no training activities with participants from 1 March to 31 August 2026. This internal declaration is not a signed certificate or independently verified attendance count. April materials evidence preparation, not delivery. The 48-person statement concerns September–October and is excluded. Source: Evenor-Tech confirmation, 21 October 2026. Pending: accountable written period corroboration and Lasith’s acceptance of declared zeros/counting rules.
NBS24.18 | Number of new jobs in green sector (Total) | 0 new jobs directly attributable to ANFORA at project start (M1). | at least 1 new full-time employment opportunity (FTE) | 0 | Declared result: 0 new jobs attributable to ANFORA in March–August 2026, confirmed internally by Evenor-Tech on 21 October. No signed HR certification is held. The official collection frequency remains annual; this six-month declaration does not establish the annual outcome. The # jobs unit and FTE target are unchanged. Pending: annual HR reconciliation and Lasith’s confirmation of annual boundaries, jobs/FTE interpretation and partial-period reporting.
RRTG.SC-01b | Number of participants in citizens engagement activities (Total) | 0 registered users at project start (platform goes live in Phase 3, M13). | Minimum of 100 registered users | 0 | Declared result: 0 eligible citizen-engagement participants, subject to Lasith’s acceptance of activity eligibility. The 5 August presentation to Vera/BALAM and Lucena City Council representatives was institutional coordination, not training or an open public citizen activity. Municipal dissemination agreed there has not materialised. Institutional representatives are not automatically counted. Sources: meeting record and Evenor-Tech confirmation, 21 October 2026; no signed eligible-attendance reconciliation is held. Pending: Lasith’s classification, participant versus 100-registered-user target mapping and repeat-counting rule.
INNOV_002 | Energy consumption of irrigation systems (kWh/ha) | Baseline per crop/farm to be measured in Phase 1 (M3–M6), subject to a formal collaboration agreement with irrigation communities in the Guadalquivir basin. | 5-10% reduction in energy consumption for irrigation |  | Not measured. Evenor-Tech confirms no irrigation electricity-consumption measurements per hectare. Water-footprint calculations cannot supply kWh/ha. Required: dated electricity readings and irrigated area for the same farms/crops and matching seasonal/annual baseline. Source: Evenor-Tech confirmation, 21 October 2026. DATA VALUE is blank; missing metering is not zero consumption.
INNOV_003 | User interaction data from digital platforms | 0 users / sessions before public launch (M13). | Continuous engagement metrics — complementary to KPI16 (100 registered users): <10 critical incidents (KPI15) and growing average session duration / return rate from M13 onwards. |  | External users/sessions not verified. Three retained PostHog CSVs show activity only on 31 August: 1 identity, 4 sessions with Pageview and 39 pageviews, as identified by the project lead, who confirms they were his own internal tests. The CSVs verify daily values/dates but omit query settings and identifiers. No external-adoption total or zero external visits can be inferred without demonstrated capture coverage. Two anonymous MongoDB calculations remain separately unclassified. Source: exports supplied 21 October and Evenor-Tech confirmation. Pending: analytics settings/coverage and Lasith’s metric and partial-coverage rules. DATA VALUE is blank; technical observations are not validated external users/sessions.
INNOV_004 | Water saved through behavioural change (litres or %) | Initial water footprint per user/recipe/diet, calculated automatically by the platform on first use (reference scenario). | 10-15% |  | Not measured. ANFORA supports water-footprint simulations, but no dated valid baseline/alternative scenario pairs are verified. Global versus Andalusian reference values do not establish supermarket versus local-market origin. Required: matched sources, quantities and servings; litres saved equal baseline minus alternative, and percentages require a valid non-zero baseline. Source: retained model/data review and Evenor-Tech confirmation, 21 October 2026. Pending: Lasith’s simulated-versus-observed reporting and aggregation rules. DATA VALUE is blank, not zero savings.
INNOV_005 | EWI: Low User Engagement Alert | No alerts before pilot tests (Activity 2.1 starts in M7). | Alert if satisfaction <80% (KPI14) or average score <4/5 (KPI19) |  | Not assessable. Evenor-Tech confirms no numerical satisfaction surveys during March–August 2026. Satisfaction percentage/mean score and the alert state cannot be evaluated. The official threshold remains satisfaction <80% or mean score <4/5. Source: Evenor-Tech confirmation, 21 October. Pending: Lasith’s missing-data representation and cohort/score rules. DATA VALUE is blank, not a zero score or a FALSE alert; later surveys cannot fill this historical gap.
INNOV_006 | EWI: Demographic Imbalance Alert | No data before platform launch (M13). Preliminary outreach to potential user sites defined in Activity 1.1 (Lucena cooperatives, markets, hospitality, cafeterias). | Balanced representation of the 6 target groups (youth <30, adults >55, long-term unemployed, farmers, agri-food industry, researchers); alert if any vulnerable group <10% of total users. |  | Not assessable. Evenor-Tech confirms insufficient demographic data for March–August 2026. Group shares and the imbalance alert require consent-based group counts and an eligible cohort denominator. The official group definitions and <10% criterion are unchanged. Source: Evenor-Tech confirmation, 21 October. Pending: Lasith’s missing-response, group-overlap and window rules. DATA VALUE is blank; no 0% shares, balanced representation or FALSE alert are inferred.