## Sheet1
D05 - ANFORA |  |  |  | 1 March – 31 August 2026
CODE | INDICATOR NAME | BASELINE | TARGET | DATA VALUE | COMMENTS
NBS4.20 | Water Exploitation Index | Guadalquivir basin WEI+ baseline to be retrieved from Eurostat/CHG at project start (M1). Andalucía is classified by the EEA as a water-scarce region with recurrent structural water stress. | 10-15% |  | DATA VALUE deliberately blank: Not measured; unavailable, not zero. Official EEA/Eurostat contextual sources located; no matched Guadalquivir baseline and follow-up attributable to ANFORA. Review territorial water-consumption and renewable-resource series using the same geography, season/year and baseline. The retrieved EEA seasonal series refers to 2023, not 2026. Required: Matched territorial baseline and follow-up, reference year/season and attribution method; clarify footprint-target versus basin-index mapping. Lasith: clarify the template ratio wording and how the 10–15% footprint-linked target applies to the territorial index; preserve the received definition until approved. [E01, E04, E05, E17]
NBS15.1 | Citizen involvement in environmental education activities (Total) | 0 (no ANFORA-led training activities prior to M13). | 50 trained users |  | DATA VALUE deliberately blank: Not verified; unavailable, not zero. Training materials exist in April. The verified September webinar and approximately 50 students in October fall after cut-off. The transcript verifies the statement of 48, not the people or their dates. Francisco says “48 trainers” at 12:40:17. At 12:40:50 Lasith requires the March–August subset; at 12:41:01–12:41:10 Francisco undertakes to check it and distinguish latest from previous training. No event/date/roster link is given. Required: Evenor-Tech/Francisco: identify whether 48 means trainers, trainees, one event or a cumulative total; supply event dates and source attendance/completion records. Reconcile eligible in-period participants and duplicates. Lasith: confirm repeated-attendance counting rule. [E03, E06, E08, E09, E14, E15]
NBS24.18 | Number of new jobs in green sector (Total) | 0 new jobs directly attributable to ANFORA at project start (M1). | at least 1 new full-time employment opportunity (FTE) |  | DATA VALUE deliberately blank: Not verified; unavailable, not zero. The earlier workbook identifies 5.45 planned person-months. No dated hiring, payroll or attributable FTE evidence was located. Compare dated HR/employment records with the declared project-start baseline. Planned team effort is not a count of newly created jobs. Required: Dated employment or contract evidence, role eligibility, hours and FTE calculation for the official annual window. [E01, E02, E04, E05, E13]
RRTG.SC-01b | Number of participants in citizens engagement activities (Total) | 0 registered users at project start (platform goes live in Phase 3, M13). | Minimum of 100 registered users |  | DATA VALUE deliberately blank: Not verified; unavailable, not zero. Coordination on 5 August and June/August outreach are evidenced. Database: one account created during the period; four earlier; five accumulated by cut-off. Account eligibility is unclassified. Reconcile eligible attendance records per event. Obtain the counting rule for repeat participants. The # participants definition and 100 registered users target remain verbatim; do not compute target attainment across these different measures. Required: Eligible citizen-engagement roster and deduplication; written clarification of participant definition versus 100-registered-user target. [E01, E03, E04, E06, E07, E11, E12]
INNOV_002 | Energy consumption of irrigation systems (kWh/ha) | Baseline per crop/farm to be measured in Phase 1 (M3–M6), subject to a formal collaboration agreement with irrigation communities in the Guadalquivir basin. | 5-10% reduction in energy consumption for irrigation |  | DATA VALUE deliberately blank: Not measured; unavailable, not zero. No farm/crop metering series, treated area or comparable seasonal baseline/follow-up was located. The food calculator produces water-footprint estimates, not irrigation electricity measurements. Use dated irrigation electricity consumption divided by irrigated area for the same farms/crops and matching season/year. Preserve the official seasonal/annual window. Required: Farm agreements and source readings, area denominator, reference season and matched follow-up. [E01, E04, E05, E10, E13]
INNOV_003 | User interaction data from digital platforms | 0 users / sessions before public launch (M13). | Continuous engagement metrics — complementary to KPI16 (100 registered users): <10 critical incidents (KPI15) and growing average session duration / return rate from M13 onwards. |  | DATA VALUE deliberately blank: Not verified; unavailable, not zero. One account created in-period, five cumulative at cut-off, and two anonymous calculation records dated 31 August are reproducible auxiliary counts. No verified external-user, unique-user, session or real-interaction total is established. Count timestamps as records only. Recover retained PostHog events and session IDs; verify deployment/coverage and identity resolution. Exclude known synthetic, internal and QA activity without assuming that residual records are external. Required: Evenor-Tech analytics owner: historical export and retention/coverage evidence, timestamp/event/identity/session fields, internal/QA exclusion register. Lasith: agree active/unique user and session definitions and reporting of partial consent coverage. [E03, E04, E10, E11, E12, E18]
INNOV_004 | Water saved through behavioural change (litres or %) | Initial water footprint per user/recipe/diet, calculated automatically by the platform on first use (reference scenario). | 10-15% |  | DATA VALUE deliberately blank: Not measured; unavailable, not zero. No comparable paired baseline/alternative/follow-up series or measured behaviour-change dataset. The fixed 2,500 L/serving comparison is not a participant baseline. Recover dated matched baseline and adjusted scenarios with consistent ingredient sources, quantities, units and servings. Calculate baseline minus adjusted footprint, and percent only with a valid non-zero baseline. Label simulation as simulation; observed consumption change is a separate claim. Required: Evenor-Tech: contemporaneous matched baseline/adjusted scenario pairs. The official definition permits simulated choices, but two unlinked anonymous records do not form a valid pair. Lasith: agree aggregation and simulated-versus-observed reporting. [E01, E03, E04, E10, E11, E13]
INNOV_005 | EWI: Low User Engagement Alert | No alerts before pilot tests (Activity 2.1 starts in M7). | Alert if satisfaction <80% (KPI14) or average score <4/5 (KPI19) |  | DATA VALUE deliberately blank: Not assessable; unavailable, not zero. Questionnaire content and a feedback/contact route exist. No validated numerical satisfaction responses, denominator, event score or executed alert result was available. Apply the original threshold, satisfaction below 80% or mean score below 4/5, to a defined completed survey cohort. An absent dataset is not a false alert or zero score. Required: Completed survey export, instrument version, denominator, event dates and a recorded alert evaluation. [E01, E03, E04, E09, E12, E13, E14]
INNOV_006 | EWI: Demographic Imbalance Alert | No data before platform launch (M13). Preliminary outreach to potential user sites defined in Activity 1.1 (Lucena cooperatives, markets, hospitality, cafeterias). | Balanced representation of the 6 target groups (youth <30, adults >55, long-term unemployed, farmers, agri-food industry, researchers); alert if any vulnerable group <10% of total users. |  | DATA VALUE deliberately blank: Not assessable; unavailable, not zero. The current User model has no age-group or employment-status fields; no verified consent-based cohort dataset was located. Student attendance does not establish age or vulnerability. Calculate each defined group share from consent-based declarations and an eligible cohort denominator; preserve the official group definitions and less-than-10% alert criterion. Required: Consented group data, reference cohort, denominator, missing-response handling and an alert evaluation. [E01, E03, E04, E11, E12, E13, E14]